TRANSFORMATION STRATEGY WORK PLAN
FY23

| Organization Name: Main Street Anytown Town, State: Anytown, State |  | Date: MM/DD/YYYY Completed by: Main Street Manager/Board Director |  |
| --- | --- | --- | --- |
| Vision: Staunton is a vibrant and vital central commercial district with secondary nodes; Wharf and Central Avenue, maintaining historic character and creating an environment for small business to thrive, supporting both residents and visitors. |  |  |  |
| Transformation Strategy #1: Community Serving |  | Transformation Strategy #2: Placemaking |  |
| Goal 1 | Goal 2 | Goal 1 | Goal 2 |
| Attract businesses that cater to all residents. i.e., grocery, pharmacy, etc. | Strategically develop Central Avenue and the Wharf with residents in mind. | Develop downtown masterplan including streetscape, parking, sidewalk, and wayfinding strategy to connect the Central business district to Central Avenue (branding opportunity) and the Wharf. | Offer diverse amenities, services, restaurants, and retail with locals and visitors in mind. |
| Lead: Ms. Main Street | Lead: Mr. Broadway | Lead: Mx. Pine | Lead: Mrs. Maple |
| Annual Responsibilities First Saturday: Monthly shopping event to showcase local businesses. Alive @ Five: Build community by raising funds for Main Street. Façade Grant: Award 5 grants during the fiscal year. Newsletter: A monthly publication released on the 1st of every month. Social Media: Update weekly highlighting events and programming to grow audience by 200 new followers while educating about organization. |  |  |  |
| Transformation Strategy #1: Community Serving |  |  |  |  |  |
| Goal 1: Attract businesses that cater to all residents. i.e., grocery, pharmacy, etc. |  | Define Success: Increase service businesses that cater to residents by 3. |  |  |  |
| Partners: City of Anytown, Chamber of Commerce, property owners |  |  |  |  |  |
| Task | Volunteer Responsible | Staff Responsible | Due Date | Progress | Budget |
| 1. Update building inventory | Mary Smith | Bob Smith | October | In Progress | $0 |
| 2. Create a list of vacant or underutilized spaces for service businesses including a small grocer. | Ann Jones | Bob Smith | November | In Progress | $0 |
| 3. Develop an incentives package. Identify needs and advocate for more resources | Jim Start | Bob Smith | December | In Progress | $250 |
| 4. Identify willing owners. | Bill Trent | Bob Smith | January | Completed | $0 |
| 5. Conduct a walking audit of the district to assess opportunities. | Josh Morgan | Bob Smith | March | In Progress | $0 |
| 6. Establish a business start-up process to make your community business friendly for start-ups | Ann Jones | Bob Smith | April | Not Started | $0 |
| 7. White-box vacant spaces for pop-ups to show proof of concept. | Mary Worth | Bob Smith | May-June | Not Started | $1500 |
| 8. |  |  |  |  |  |
|  |  |  |  | Total | $1750 |
| Transformation Strategy #1: Community Serving |  |  |  |  |  |
| Goal 2: Strategically develop Central Avenue and the Wharf with residents in mind |  | Define Success: Brands established for nodes and drawing 200 new resident visits each month. |  |  |  |
| Partners: City of Anytown, Planning Department, Zoning Department, property owners |  |  |  |  |  |
| Task | Volunteer Responsible | Staff Responsible | Due Date | Progress | Budget |
| 1. Survey residents on vision for nodes to establish brand themes. | Mary Smith | Bob Smith | October | In Progress | $100 |
| 2. Hold public meetings on suggested brands for nodes. | Ann Jones | Bob Smith | November | In Progress | $0 |
| 3. Develop a personality and brand voice for each node. | Jim Start | Bob Smith | December | In Progress | $0 |
| 4. Create a brand story and brand name for destinations. | Bill Trent | Bob Smith | January | Completed | $0 |
| 5. Pick brand look, logo, and color palette. | Josh Morgan | Bob Smith | March | In Progress | $500 |
| 6. Build effective branding communications strategy. | Ann Jones | Bob Smith | April | Not Started | $0 |
| 7. Tell compelling stories | Mary Worth | Bob Smith | May-June | Not Started | $200 |
| 8. Integrate brands with organization marketing and launch. | Ann Jones | Bob Smith | April | Not Started | $300 |
| 9. |  |  |  |  |  |
|  |  |  |  | Total | $1100 |

| Transformation Strategy #2: Placemaking |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Goal 1: Develop downtown masterplan including streetscape, parking, sidewalk, and wayfinding strategy to connect the Central business district to Central Avenue (branding opportunity) and the Wharf. |  | Define Success: Awarded a grant to match City funding for downtown masterplan. |  |  |  |
| Partners: City of Anytown, Grant Funder, State Transportation Department, City Public Works |  |  |  |  |  |
| Task | Volunteer Responsible | Staff Responsible | Due Date | Progress | Budget |
| 1. Research grant opportunities for master planning | Mary Smith | Bob Smith | October | In Progress | $0 |
| 2. Apply for master planning grant. | Ann Jones | Bob Smith | November | In Progress | $200 |
| 3. Announce the award of grant. Thank partners. | Jim Start | Bob Smith | December | In Progress | $0 |
| 4. Issue an RFP for master plan. | Bill Trent | Bob Smith | January | Completed | $0 |
| 5.Establish committee to review RFPs and award contract. | Josh Morgan | Bob Smith | March | In Progress | $0 |
| 6. |  |  |  |  | $0 |
| 7. |  |  |  |  | $0 |
| 8. |  |  |  |  | $0 |
|  |  |  |  | Total | $200 |
| Transformation Strategy #2: Placemaking |  |  |  |  |  |
| Goal 2: Offer diverse amenities, services, restaurants, and retail with locals and visitors in mind. |  | Define Success: Activated 1 underutilized space for students. |  |  |  |
| Partners: College Administration and Student Leadership, City of Anytown, Public Works, property owners, Arts Council |  |  |  |  |  |
| Task | Volunteer Responsible | Staff Responsible | Due Date | Progress | Budget |
| 1. Host of meeting with College Student Leadership to engage students in a downtown project. | Mary Smith | Bob Smith | October | In Progress | $0 |
| 2. Work with student committee to design project. | Ann Jones | Bob Smith | November | In Progress | $0 |
| 3. Identify property and owners for project. | Jim Start | Bob Smith | December | In Progress | $0 |
| 4. Assemble project and launch. | Bill Trent | Bob Smith | January | Not Started | $750 |
| 5. Share a compelling story about the project and building community with the students. | Jim Start | Bob Smith | December | In Progress | $0 |
| 6. |  |  |  |  | $0 |
| 7. |  |  |  |  | $0 |
| 8. |  |  |  |  | $0 |
|  |  |  |  | Total | $750 |